## Form Responses 1
Timestamp | Role | Location | Current employee | Age | What is the one main cause of project failure in your opinion? | How many software projects have you worked on? | How many of those projects were completed on time? | Not completed on time | % not completed on time | What are a few causes (top 3 - mention in order) of project delays in the software industry? | Who are the people responsible for software project delays? | Which phase of SDLC do you think is the causing maximum delays in the projects? | Any experience related to software project delays that you would like to share
2023-05-31 12:11 | Software Developer | Bangalore | Yes | 21-30 | Delayed Projects often fail | 4 | 2 | 2 | 50% | 1 - Incorrect estimation 2 - lazy employees 3 - Changing requirements midway | Project Manager | Planning and Estimation
2023-05-31 12:17 | Team Lead | Bangalore | No | 21-30 | Scheduled Delays | 8 | 3 | 5 | 62.5% | Lack of proper planning budget issues unnecessary approvals deployment issues lack of motivation among team members lack of skilled professionals | I think its on the entire team and not one person can be responsible | Planning and Estimation | Although I do think that planning is where a project's fate is decided with respect to delays, I have experienced a situation wherein the project was delayed due to deployment issues. Because of an incorrect deployment that was done not only was the project delayed but it caused a major outage in one of the customer-serving databases.
2023-05-31 12:22 | Database Engineer | Mumbai | Yes | 51-60 | Lack of proper resources including time, money and effort | 3 | 3 | 0 | 0% | unmotivated team members lack of budget inadequate design inadequate testing | Team members | Design | I have changed my field into software after working for a long time in teaching profession so probably I am not the right person to answer this survey. What I can say from my experience is that if your team is not motivated enough it leads to various issues, project delays being one of them.
2023-05-31 14:31 | Associate Software Developer | Hyderabad, India | Yes | 21-30 | Overestimated dealines | 3 | 1 | 2 | 66.67% | 1. Planning phase not detailed enough 2. Sometimes, not everyone is on the same page in a team in terms of the technical acumen required for the project 3. Errors not resolved efficiently | Project Manager | Planning and Estimation
2023-06-01 09:53 | Software Developer | Manila | Yes | 21-30 | Delayed projects fail | 3 | 1 | 2 | 66.67% | expertise of team members testing code reviews approvals from various teams | Project Manager | Testing
2023-06-01 10:44 | Senior Manager | Melbourne | Yes | 51-60 | Budget issues | 10 | 8 | 2 | 20% | Estimation planning requirement change | Client | Planning and Estimation | Alot of times the client requirements change over time and that leads to significant delays in projects
2023-06-01 10:46 | Team Lead | Melbourne | Yes | 31-40 | project delays | 5 | 2 | 3 | 60% | Planning and estimation lack of proper resources lack of proper assistance by clients | Project Manager | Planning and Estimation
2023-06-01 10:50 | Software Developer | Seattle | Yes | 21-30 | scheduled delays | 4 | 3 | 1 | 25% | lack of proper requirement gathering and planning untimely code reviews client vision expertise of the team members | Team members | Analysis and Requirement Gathering
2023-06-01 10:56 | Software Developer | Boston | Yes | 21-30 | budget issues | 7 | 3 | 4 | 57.14% | improper planning vague requirements tight deadlines lack of proper testing and quality checks | Team members | Planning and Estimation
2023-06-01 10:58 | Software Developer | Boston | Yes | 31-40 | budget issues | 3 | 2 | 1 | 33.33% | lack of proper testing improper project planning improper project tracking requirement changes during project timelines | Project Manager | Testing
2023-06-01 11:04 | Senior Manager | San Francisco | Yes | 31-40 | project delays | 5 | 2 | 3 | 60% | improper planning correct people are not involved in the estimation tight deadlines requirements changing midway | Team members | Planning and Estimation
2023-06-01 11:07 | Software Developer | Manila | Yes | 41-50 | budget issues | 7 | 4 | 3 | 42.86% | improper planning insufficient testing design changes requested by client midway improper transition between members | Project Manager | Analysis and Requirement Gathering
2023-06-01 11:12 | Project Manager | Bangalore | No | 41-50 | project delays | 6 | 2 | 4 | 66.67% | tight schedules due to budget constraints lack of technical knowledge and coordination among employees untimely approvals on various things improper risk management plans | Team members | Design
2023-06-01 11:18 | Software Developer | Bangalore | No | 31-40 | project delays | 3 | 0 | 3 | 100% | improper planning untimely execution by development and testing teams tight schedules | Team members | Design | In my experience, if the project is delayed from the start then it just goes on to get delayed. So it is better to start early and get your requirements cleared
2023-06-01 11:21 | Project Manager | San Francisco | Yes | 51-60 | project delays or budget issues | 10 | 6 | 4 | 40% | improper estimation or rather overestimation improper risk management plans improper project tracking improper requirement gathering | Project Manager | Planning and Estimation | Project tracking is an key thing that managers often overlook which causes most projects to get delayed even if they start on time. I learnt this the hard way early on in my career when a couple of projects started well but because I lost track on those people started getting complacent and the work was delayed
2023-06-01 11:24 | Software Developer | Bangalore | No | 21-30 | improper project planning and tracking | 3 | 1 | 2 | 66.67% | improper project planning and tracking tight schedules lack of expertise in the employees improper expectation setting with the client in the beginning lack of proper testing schedules | Project Manager | Planning and Estimation
2023-06-01 11:29 | Tester | Bangalore | Yes | 31-40 | budget issues | 6 | 2 | 4 | 66.67% | lack of proper planning delay in code compilation by the development team requirement changes in between inadequate resource allocation | Team members | Development | Most of the times the project was delayed because we weren't given the code by the development team on the exact dates we were supposed to start the testing. Due to this issue testing was delayed and therefore the project. Also if the requirements changed midway the entire team had to redo the test cases we had prepared and that took a significant amount of unaccounted for time.
2023-06-01 13:12 | Program Manager | Melbourne | Yes | 51-60 | improper allocation of resources | 10 | 6 | 4 | 40% | inadequate resource allocation improper risk management strategies unmotivated members interference of third party vendors | Project Manager | Planning and Estimation
2023-06-01 14:05 | Software Developer | Bangalore | Yes | 21-30 | improper project management | 3 | 1 | 2 | 66.67% | losing key development members tight schedules late approvals for alot of things | Project Manager | Planning and Estimation | The loss of a team member has more gravity and effect, especially if the person is a key player in your project. The result may lead to a delay.
2023-06-01 14:14 | Project Manager | Melbourne | Yes | 31-40 | improper project management | 7 | 4 | 3 | 42.86% | improper management talent drain during the project improper knowledge transfer or handover overestimation of timelines issues with third-party integrations lack of communication between various teams and its members | Project Manager | Development | Choosing the correct technologies and methodologies is an important task in my opinion to reduce project delays. Alot of time is wasted in integrating components only to realize better alternatives were available. This does not always work because some systems are sensitive like healthcare and banking. These do require a specific set of technical tools to be used so as to make them secure and prevent data leaks.
2023-06-01 14:23 | Team Lead | Melbourne | No | 21-30 | project delays | 4 | 1 | 3 | 75% | delay caused due to improper testing and QA lack of communication among teams change in scope of the project requirements approval issues wrong development methodology tight project timelines uncooperative clients | Team members | Testing
2023-06-01 14:27 | Software Developer | Seattle | No | 31-40 | project delays | 5 | 3 | 2 | 40% | Improper Planning Third party integrations requirement changes lack of coordination between teams talent drain of developers or testers | Project Manager | Planning and Estimation
2023-06-01 14:40 | Software Developer | Mumbai | Yes | 31-40 | project delays | 4 | 3 | 1 | 25% | Lack of proper project management talent drain incorrect planning missing accountability between team members | Client | Planning and Estimation
2023-06-01 14:42 | Team Lead | Bangalore | Yes | 21-30 | incorrect planning | 5 | 2 | 3 | 60% | improper planning letting go of trained developers unclear understanding or expectations of business requirements | Project Manager | Planning and Estimation

## Sheet1
Role | Role of the professionals
Software Developer | 12
Project Manager | 6
Data Professionals | 1
Team Lead | 4
Tester | 1
Location | Location of the professionals
Bangalore | 8
Hyderabad | 1
Mumbai | 2
Melbourne | 5
Manila | 2
Boston | 2
San Francisco | 2
Seattle | 2
Gender | Gender Distribution
Male | 11
Female | 13
Phase | Phase causing project delays
Planning and Estimation | 14
Analysis and Requirement Gathering | 2
Design | 3
Development | 2
Testing | 3
Deployment and Maintenance | 0
people | People Responsible
Team Members | 8
Project Managers | 13
Client | 2
Entire Team | 1
Third-Party vendors | 0

## Sheet4
Causes of project delays | Points | Percentage
Improper planning and estimation | 22
Requirement changes or changes in the scope of the project | 15
Lack of skilled employees or talent drain | 12
Lack of coordination or cooperation among team members | 8
Inefficient testing process | 7
Tight schedules and deadlines | 7
Unmotivated and unaccountable team members | 5
Unecessary approval process | 5
Unclear client vision | 5
Budget issues | 3
Lack of proper resources | 3
Inefficient requirement gathering | 3
Incorrect project tracking | 3
Inadequate risk management strategies | 3
Interference or issues of third-party vendors | 3
Code reviews | 2
Improper transition or knowledge transfer between team members | 2
Development issues | 2
Deployment issues | 1
Inadequate design process | 1
112
Classes
Planning factors | 46
Implementation factors | 39
Human factors | 27

## Sheet2
% not completed on time |  | Number of people whose projects were delayed
50% | less than 40% of the projects delayed | 8
62.5% | 40% - 60% projects delayed | 6
0% | greater than 60% projects delayed | 10
66.67%
66.67%
20%
60%
25%
57.14%
33.33%
60%
42.86%
66.67%
100%
40%
66.67%
66.67%
40%
66.67%
42.86%
75%
40%
25%
60%